Master Scenario Events List (MSEL) for Region 6 Water Rescue

Full Scale Exercise

August 26, 2017-Lake Ravine

Beginning promptly at 0900, the Exercise Director/Senior Controller will notify 4-2 Dispatch of a car losing control and entering the lake near the Izaac Walton League boat ramp. Dispatch will call out HPD, HFD, and Beadle County Search and Rescue.

Scenario Summary

The Scenario utilized for this exercise is based on a Water Rescue Incident within the County, which results in requesting mutual aid from all Region 6 Counties.

The Scenario utilized for this exercise is based on a car losing control and entering the lake near the Izaac Walton League boat ramp at approximately 0900 on 26 August 2017. A man fishing on the lake at the time calls 911 to report the accident. 4-2 Dispatch alerts the HPD and HFD to respond. 4-2 will then call out Beadle County Search and Rescue.

Strong winds and possible rain in the forecast will make the recovery difficult. In anticipation of a lengthy dive recovery mission, Beadle County will make an official request for mutual aid from the Davison, Brookings and Yankton Dive Teams.

The fisherman saw two occupants in the car, who will be recovered from the car and transported by ambulance if within the recovery time, or by the coroner to the county morgue.

The Huron Fire Department will request a HAZMAT Team to address contamination of the lake, due to a thin coat of what appears to be gasoline/oil in the water. The HAZMAT Team will need to address the fuel, but at the same time allow the dive team to recover the remaining bodies.

Several boats and jet-skis on the lake begin to observe the rescue mission. Concerned family members arrive on scene to determine the status of the passengers, of which may have already been transported to the local hospital or morgue. The scene will become chaotic in a short time, and crowd control on land and in the water will be an issue.

The Beadle County Dive Team finds the vehicle, but is exhausted and requests another dive team take over the mission. The Davison, Brookings and Yankton Dive Teams will rotate in the water searching for the bodies.

Master Scenario Events List (MSEL)

| Inject # | Inject Time | Inject Origin (From) | Inject Destination (To) | Inject Description | Expected Action |
| --- | --- | --- | --- | --- | --- |
| 1 | 0900 | Controller | Dispatch | Notify Dispatch of an accident, request Police, Fire/EMS assistance. | Dispatch will simulate a 911 call: “THIS IS AN EXERCISE. Officers, Fire/EMS needed for a one vehicle accident, which went into Lake Mitchell SE of the west end boat ramp, with an unknown number of occupants”. THIS IS AN EXERCISE. Incident Commander will request ambulance, and notify coroner of possible mass fatality incident. |
| 2 | 0902 | Controller | County Emergency Manager (s) | Request Davison County EM mobilize Search and Rescue and bring the MEOC. | County EM will request Dispatch send out a call out page to all S.A.R. Members: “THIS IS AN EXERCISE. S.A.R. Members: Report to the shed, take all available equipment needed to extract a vehicle and occupants from Lake Mitchell. Location is near the west end boat ramp.” THIS IS AN EXERCISE. |
| 3 | 0905 | Controller | Incident Commander | Inform ER of possible admissions. | Incident Commander will request Dispatch to notify the ER of possible admissions/fatalities. |
| 4 | 0910 | Controller | Incident Commander | Request HAZMAT Team | Incident Commander will request MEOC staff to coordinate a HAZMAT Team. |
| 5 | 0912 | Controller | County Emergency Manager | Initial Notification to the Duty Officer | County EM will inform the Duty Officer and Regional Coordinator of the incident. More information will be relayed at a later time. |
| 6 | 0930 | Controller | Incident Commander | Region 6 channel overload. Request Special OPS Channel. | Request made (denied). |
| 7 | 0935 | Controller | Incident Commander | Request Coroner | MEOC Staff notify coroner of 3 assumed fatalities. |
| 8 | 0940 | Controller | Incident Commander | Family members arriving on scene looking for their family. | Incident Commander will utilize Search and Rescue and local Police/Sheriff’s Office to block off the scene and escort the family members to an assigned location. |
| 9 | 0945 | Controller | Incident Commander | Communication failure. | Logistics rectify the problem. |
| 10 | 0955 | Controller | Dive Team Commander | Dive Team member is experiencing shortness of breath and rapid heartbeat. | Notify EMS to have diver evaluated. |
| 11 | 1000 | Controller | Dive Team Commander | Divers exhausted. Request mutual aid. | Dive Team Commander will request mutual aid from Beadle, Brookings and Yankton Dive Teams. |
| 12 | 1015 | Controller | Dive Team Commander | Boats/Jet-Skis getting too close to the scene, endanger divers. | Dive Team Commander will request water security move the perimeter back. |
| 13 | 1030 | Controller | County Emergency Manager | Duty Officer requests SITREP | MEOC staff will contact Duty Officer with updated information. |
| 14 | 1040 | Controller | Public Information Officer | News Media are on scene and want information. | PIO will deliver a statement to the media. |
| 15 | 1100 | Controller | Incident Commander | Time Jump to 1700 | Simulate time jump to 1700, loss of daylight, fresh personnel required. |
| 16 | 1105 | Controller | Incident Commander | Power failure on MEOC Generator. | Logistics switch MEOC to back-up Generator, then rectify the problem. |
| 17 | 1115 | Controller | County Emergency Manager | Incident Commander will need 6 light sets and generators, assuming the recovery will go into dark. | Incident Commander will request MEOC to coordinate light kits from Search and Rescue. |
| 18 | 1130 | Controller | County Emergency Manager | Duty Officer requests SITREP | MEOC staff will contact Duty Officer with updated information. |
| 19 | 1200 | Controller | Dive Team Commander | Rescue boat will not start. Is anchored in the lake. | MEOC staff will coordinate boat towed to shore. |
| 20 | 1215 | Controller | Incident Commander | News Media and observers are not staying behind roped off area. | IC will have the MEOC Staff ensure all are in the roped off area. |
| 21 | 1220 | Controller | Incident Commander | One observer experiences an unknown medical issue, becomes dazed and confused. | EMS on site will evaluate. |
| 22 | 1230 | Controller | Public Information Officer | News Media request an update. | PIO will deliver a statement to the media. |
| 23 | 1245 | Controller | Incident Commander | National Weather Service has issued a Severe Thunderstorm Warning, to include lightening issued for Davison County. Severe chop develops on Lake Mitchell. | Dive Team Commander will pull all divers from the water, wait out the storm, continue recovery mission. |
| 24 | 1300 | Controller | Incident Commander | Time Jump to 2300 | Simulate time jump to 2300, fresh personnel required. |
| 25 | 1315 | Controller | Incident Commander | Incident Commander requires a tow truck to remove vehicle. | Incident Commander contacts MEOC to coordinate local towing company. |
| 26 | 1330 | Controller | Incident Commander | Power failure on MEOC Generator, again. MEOC starts on fire and is destroyed. | MFD extinguishes fire, No back-up MEOC available, operation run from the ground/vehicles. |
| 28 | 1415 | Simcell | MEOC | Situation Update – End of Exercise, Hotwash & Reporting | Conduct Hotwash and evaluation materials at MEOC. |
|  | 1500 |  |  | END OF EXERCISE - DEMOB |  |

# Text boxes

INTRODUCTION